## DTT Test Hour Log
Instruction: Fill in the number of hours that were required to complete the test. Please include every step you took during the process and include a detailed description of every step. Add reasoning on why you took certain decisions or applied specific techniques. We prefer quality over quantity so take your time with the test and the log.
Subject | Amount of hours | Date | Description | Bonus
Project Initialization | 2 | 22/08/2025 | Set up the project using Vite + vue + TypeScript. Created a scalable folder structure (components, pages, services, types, themes)and routing for maintainabilit
Theme System & Global Styles | 1 | 22/08/2025 | Applied consistent global styles to ensure visual coherence across the app.
Create Page Implementation | 2 | 22/08/2025 | create a createhouse page and seperate all the code to make the main componet smaller
Component Design System | 1 | 23/08/2025 | Developed reusable components
API Consumption & Logic | 1.5 | 23/08/2025 | Created Axios service layer with custom hooks Managed loading, error, and success states. Ensured clean separation of concerns and scalability.
Error Handling Strategy | 1 | 23/08/2025 | implement the error Handling
House Listing Page | 2 | 24/08/2025 | Displayed dynamic data using reusable components.
Responsive Design | 1 | 24/08/2025 | Applied mobile-first design using media queries and flexible layouts.
Edit Page Implementation | 2 | 24/08/2025 | Created update page with pre-filled form and update logic.
About Page & Icons | 1 | 24/08/2025 | Developed a static AboutPage
File Upload Bug Fix | 2 | 24/08/2025 | Resolved a file upload issue
extra filter "made by me" | 1 | 24/08/2025 | Added a custom filter to the listing page | x
Total amount of hours | 16.5